## Slide 1: Milestone Five
Florida Tech IGVC

## Slide 2: Milestone 5 Matrix
# | Task | % Complete | Brent | Adam | Chris | Will
1 | LiDAR & Lines | 75% | 0% | 15% | 85% | 0%
2 | Software Integration | 67% | 25% | 25% | 25% | 25%
3 | Software Testing | 50% | 25% | 25% | 25% | 25%
4 | Hardware Integration | 25% | 25% | 25% | 25% | 25%
5 | Motion Planning | 100% | 100% | 0% | 0% | 0%
6 | GUI | 75% | 100% | 0% | 0% | 0%
7 | Startup, Control, Logging | 50% | 10% | 20% | 0% | 70%
8 | Comm. Maintenance | 100% | 10% | 10% | 10% | 70%
9 | IOP | 0% | 0% | 70% | 0% | 30%
10 | Create Poster | 100% | 25% | 25% | 25% | 25%

## Slide 3: Navigation & GUI
D* Lite implementation complete
  Dimension concerning orientation added
  Significant speed and accuracy improvement
Next Steps:
  Short sim for testing
  Interface for incoming lines and obstacles
  Live testing

## Slide 4: Line Detection
Line detection on course-like conditions functional
  Some issues with half-sun, half-shade images
  Able to see obstacles
Polarizing film reduces glare significantly
Next steps
  Converting lines into format understandable by motion planner
  Working with half and half images
  Potentially working on obstacle detection

## Slide 5: Line Detection Video

## Slide 6: Communication
Interface for ROS written
C++ components cleaned up
Next Steps
  Get FSU to post their code
  Write unit for LiDAR

## Slide 7: Integration & Testing
Still developing code
Integration with ROS tested
FSU not allowed to send LiDAR
Robot not shipped
Next steps
  Get the robot
  Write short sim for motion planner

## Slide 8: Position
INS ROS node operational
Robot localization taking encoder values and GPS data
Potentially use triangulation within the motion planner or using the LiDAR to get absolute position
Next steps
  FSU is benchmarking the INS
  Begin looking at triangulation / trilateration

## Slide 9: Milestone 6 Matrix
# | Task | Brent Allard | Adam Hill | Chris Kocsis | Will Nyff.
1 | LiDAR & Lines | 0% | 25% | 75% | 0%
2 | Testing & Integration | 25% | 25% | 25% | 25%
3 | Motion Planning & GUI | 100% | 0% | 0% | 0%
4 | Startup, Control, & IOP | 10% | 60% | 0% | 30%
5 | Comm. Maintenance | 10% | 10% | 10% | 70%
6 | Demo Video | 25% | 25% | 25% | 25%
7 | Documentation | 25% | 25% | 25% | 25%